## Tasks
Task ID | Task Name | Task Description | Staff Involved | Task Estimated Time (Hours)
| Research for City Tour Providers | The purpose here is to contact different tourism companies asking for budget for a 1-person tour that can do the city tour in Centro Historico in Córdoba Argentina in English. | Director
| Request Proper Permission | This task consists in obtaining the proper clearance so we can shoot in the intended locations. | Director
| Create the script | The writter/author will create the script taking into account the intention of this film which is creating a dynamic/interactive tour guide through historic points accross Cordoba city. | Writter
| Create the story board based on the script. | The designer will create sketches presenting the dynamics of how this tour guide will be told to the users. | Designer/Writter/Author
| Kick off project with the team | Introduce team members so the understand what they are shooting and the dynamics to use to create the film. | All
| Prepare Film Equipment at location | Here all the equipment should be prepared at the first location where the first scene will be recorded. | Camera Man
| Shoot Scene in San Martín Square | Here the film creation take places at the different locations. The tour guide and interviewer should follow the director's intructions according to the script defined. | Camera Man, Director, Interviewer, Tour Guide
Shoot Scene in The Cathedral Entrance
Shoot Scene in The Cathedral Interior
Shoot Scene in Cabildo's Plaza Mayor
Shoot Scene in Cabildo's Plaza Menor
Shoot Scene in Cabildo's Prison
| Post Production Work from Raw Material | At this point, all the story was shooted and now the post production engineer will create the film according to the director's instructions. In this step, the engineer must make the different objects selectable in the film so the user can interact with them. | Post Production Engineer, Director
| Film Wrap Up | At this point, the material is ready to be presented to a marketing team so they can propose the best way to sell this product. | All

## Staff
Role | Description | Estimated Amount of Hour Needed
CAMERA MAN | This person will be responsible for shooting the video following the directions of the director | 12
DIRECTOR | This person will be responsible for defining how the film will be created based on the script.and story board | 120
POST PRODUCTION EDITOR | This person will be responsible for creating the finalized video from the raw material created during the film. | 120
WRITER | This person will be the one creating the story and the script. This person will work together with the director and designer. | 40
DESIGNER | This person is responsible for creating the story board. This person will work together with the writer and director. | 40
TOUR GUIDE | This person will be responsible of conducting the tour guide. | 5
INTERVIEWER | This person will be responsible of walking the city with the tour guide asking questions as a regular visitor. | 5
PRODUCER | The person/company paying for the expenses that involves creating the material. | 40
| TOTAL | 382 | Hours

## Budget
Item | Unit Price (USD) | Price (USD)
8 GOPRO HERO 5 CAMERA | 350 | 2800
RIG FOR 8 CAMERAS | 600 | 600
TRIPOD | 150 | 150
GIMBAL STABILIZER | 1000 | 1000
KOLOR AUTOPANO VIDEO PRO 2 | 650 | 650
ADOBE PREMIERE (1 YEAR) | 30 | 360
LAPTOP FOR COMPUTER-RELATED WORK (2) | 2000 | 4000
TOUR GUIDE | 200 | 200
SALARIES (Estimated Hour Rate = U$D: 30) | 382 | 11460
MISC (Rent Furniture, Rent Place to work, etc.) | 8000 | 8000
TOTAL |  | 29220